## Project Information
PROJECT INFORMATION
Field | Value
Project Name | SYLTHARAE-Pro
Status | Working
Project Type | Repair and quality assurance of an existing software product: a web application that finds, reads, extracts and connects information from large mixed collections of files (documents, spreadsheets, e-mail, archives, images, audio, video, e-books, databases and diagrams).
Priority | High
Intermediary | An artificial-intelligence coding agent working inside the repository owner's own workspace, under the owner's direction and account. Every saved change in the project carries the owner's name.
Yes | Yes. The work described in the task register was carried out by an AI agent acting for the owner: it inspected the software, ran the checks, wrote the repairs and recorded the evidence. The owner set the rules of engagement, approved the repairs and kept the final decisions.
Expected Start Date | 2026-10-23
Expected End Date | Unverified
Expected End Date is recorded as Unverified because no plan anywhere states a completion date. Using today's date would have invented one. An amber cell means the value is an estimate or is not evidenced; the Task Register uses the same marking.

## Task Register
Subject or Tasks | Project | Type | Does it fall under a group? | Status | Priority | Main Task (Original/Parent) | Expected Start Date | Expected End Date | Details and Task Description
1.0 Stage: environment, audit record and tools | SYLTHARAE-Pro | Planning | 1. Getting set up: environment, audit record and tools | Completed | High | - (top-level task) | 2026-10-23 | 2026-10-24 | The opening stage, covering the first two days. The software's existing code was put under version control so every later change could be compared against it; a working test environment (programming runtime, database server and a real browser) was built from nothing; the whole application was surveyed and its problems recorded; and the automated checking tools that every later claim depends on were written. Everything in this stage is finished.
Put the existing application under version control and start a separate repair branch | SYLTHARAE-Pro | Setup | 1. Getting set up: environment, audit record and tools | Completed | High | 1.0 Stage: environment, audit record and tools | 2026-10-23 | 2026-10-23 | The application is large - roughly four thousand files and about five hundred and sixty thousand lines - and it arrived with no usable history: it was captured in a single step, so there was no record of what changed, when or why. That single capture became the fixed reference point, and all repair work was placed on a separate branch so that nothing on the main line changed while the work was being done. The software identifies itself as version 2.2.0, which is a declared version number rather than a released one.
Build a working test environment: programming runtime, database server and a real browser | SYLTHARAE-Pro | Setup | 1. Getting set up: environment, audit record and tools | Completed | High | 1.0 Stage: environment, audit record and tools | 2026-10-23 | 2026-10-24 | The software cannot start without a database server, and it cannot be judged properly without a real browser. The starting machine had neither. A Python environment was assembled from the project's own list of required packages, a PostgreSQL 16.2 database server was started from a portable package, and a Chromium browser was made to run without a screen by supplying the missing system libraries as stand-ins, so pages could be loaded and buttons really clicked. The machine forgets everything between sessions, so this was rebuilt repeatedly, and the rebuild was written down step by step so it is repeatable rather than guesswork.
Survey the whole application and record, in plain terms, what is broken | SYLTHARAE-Pro | Research | 1. Getting set up: environment, audit record and tools | Completed | High | 1.0 Stage: environment, audit record and tools | 2026-10-23 | 2026-10-24 | A first full survey of the software was produced: what it is meant to do, how it is built, which interfaces it offers to users and to other systems, and what could not be checked at all. Seven problems were recorded, each with the exact steps that reproduce it, the underlying cause, what it means for a real user, and a suggested repair. The four most serious were: the software cannot start unless a database server is already running; its changelog describes database changes that do not exist in the code; the existing test suite could not be run; and no real browser testing was possible at all. Every entry states how it was established.
Build the automated checkers, probes and measuring tools used for every later claim | SYLTHARAE-Pro | Tooling | 1. Getting set up: environment, audit record and tools | Completed | High | 1.0 Stage: environment, audit record and tools | 2026-10-24 | 2026-10-24 | Twenty-nine small programmes were written so that statements about the software could be produced by a machine rather than by reading code and forming an opinion. They list every web address the application publishes; send valid, missing, malformed and other people's identifiers to every address that accepts one; fire hostile query strings and broken request bodies; check that database statements match the real database and that screens are wired to the code behind them; count and time real queries; inject failures such as a full disk or a killed process; and operate the real browser. These tools produced nearly every number in this register.
2.0 Stage: first three rounds of verification and repair | SYLTHARAE-Pro | Verification | 2. First three rounds of verification and repair | Completed | High | - (top-level task) | 2026-10-23 | 2026-10-24 | Stage covering the first three verification rounds: run the existing test suite, repair what it exposed with a test that pins each repair, then replace opinion with measurement by generating complete lists of everything the software contains, with a verdict on every single entry. Finished within two days.
Repair the first defects the existing test suite exposed, one test per repair | SYLTHARAE-Pro | Testing | 2. First three rounds of verification and repair | Completed | High | 2.0 Stage: first three rounds of verification and repair | 2026-10-23 | 2026-10-23 | The existing test suite was run properly for the first time: 4,320 tests, of which 121 failed, 12 could not even start and 134 were skipped. The first genuine defect was repaired: the software recorded progress messages using a list of twenty-one message types while the database accepted only eleven of them, so honest warnings could not be stored at all and the write was rejected. The two lists were reconciled and a dedicated test now fails if they ever drift apart again. A self-check that reports whether the installation is healthy gave thirty-one checks and no failures once the database it expects existed; that gap was a setup problem, not a product defect, and is recorded as such.
List every interface, database statement and text string, and give each one a verdict | SYLTHARAE-Pro | Verification | 2. First three rounds of verification and repair | Completed | High | 2.0 Stage: first three rounds of verification and repair | 2026-10-24 | 2026-10-24 | Instead of sampling a few files, the software's own machinery was interrogated by script to produce twelve complete lists: web addresses (485, plus 342 exercised at run time), user-facing interfaces (35), page templates (79), database tables and columns (40), database statements (2,324), translatable text identifiers (7,141), configuration settings (68), stylesheets (45), browser scripts (178) and modules (422). That is 11,188 entries. Every entry was given one of six verdicts - verified working, repaired with a test, defect open, needs a decision, blocked by the environment, or unused code - and not one was left unexamined.
Repair the reporting screens, alerts, priorities, background jobs and access gaps | SYLTHARAE-Pro | Development | 2. First three rounds of verification and repair | Completed | High | 2.0 Stage: first three rounds of verification and repair | 2026-10-24 | 2026-10-24 | Thirteen repairs in one batch. Report screens now render on the server and can export a case dossier. Alerts show the text that was actually stored instead of a mismatched label. Identifier detection uses one consistent record type. The priority ladder is now identical in the database query and in the application code, capped at high for outcomes, with the reason for each priority stored alongside it. A cancelled job is marked by a flag, and its progress messages are translated into the vocabulary the database accepts. A user's mistake now returns a clear client error instead of an internal server error, and the settings export is restricted to administrators. Document reading no longer writes columns that do not exist and keeps the reason a record is partial. Two screens gained their missing main heading, one screen posted to the wrong address, and a refused scenario definition now answers with a clear explanation rather than a bare failure.
3.0 Stage: Round 4 - probing and measuring the running system | SYLTHARAE-Pro | Measurement | 3. Round 4: probing and measuring the running system | Completed | Medium | - (top-level task) | 2026-10-24 | 2026-10-24 | Stage covering the round in which the audit stopped being a reading exercise. Every route was attacked with real requests, hostile input was fired at every search box, a realistic hundred-thousand-record database was loaded and measured, and the system was deliberately broken mid-work to see what it does. The round ended with a written list of the problems found and the decisions the owner needed to make.
Send valid, missing, broken and other-people's identifiers to all 155 addresses that take one | SYLTHARAE-Pro | Verification | 3. Round 4: probing and measuring the running system | Completed | High | 3.0 Stage: Round 4 - probing and measuring the running system | 2026-10-24 | 2026-10-24 | Six hundred and sixty attempts across one hundred and fifty-five web addresses that accept an identifier. None produced another user's data, a server error or a stack trace. Nine addresses answered 'not implemented', which is correct for features that are declared but not built. Sixty-five could not be tried because the test data they need did not exist; those are recorded as untested, never as passing. As a control, the same probe was run against an earlier state of the code, where it produced eight genuine findings, all since repaired - which is what shows the probe can actually find things.
Fire deliberately hostile input at every search, filter and paging control, and fix what breaks | SYLTHARAE-Pro | Testing | 3. Round 4: probing and measuring the running system | Completed | Medium | 3.0 Stage: Round 4 - probing and measuring the running system | 2026-10-24 | 2026-10-24 | 6,440 hostile query strings were sent to every screen that accepts search, sorting, filtering or paging options: no findings and no stack traces. The companion sweep with deliberately broken request bodies found real problems and produced repairs. Control characters and non-object data are now refused before reaching the database. Asking for a page far beyond the end returns an empty page instead of a server error. Numbers arriving from a typed address are read without trusting them. Creating a duplicate name answers with a clear conflict message. Cache statistics report fingerprints instead of the database queries being cached. The notification page-size limit now matches the limit the software itself states.
Measure the system under a realistic 100,000-record load, then kill it in the middle of work | SYLTHARAE-Pro | Measurement | 3. Round 4: probing and measuring the running system | Completed | High | 3.0 Stage: Round 4 - probing and measuring the running system | 2026-10-24 | 2026-10-24 | A database was loaded with a hundred thousand records and the ten heaviest queries were timed in detail, together with how many separate queries each screen issues. Behaviour under failure was then tested by stopping the database during an import and by killing and restarting the application in the middle of a job, to see what the user is told and whether work is lost. The results changed the plan: the heaviest queries each read two large tables in full, three sorting operations spill to disk, and the time an import takes grows faster than the file does above roughly half a megabyte.
Add tests for four repairs that had shipped without one, and fix three broken screens | SYLTHARAE-Pro | Testing | 3. Round 4: probing and measuring the running system | Completed | High | 3.0 Stage: Round 4 - probing and measuring the running system | 2026-10-24 | 2026-10-24 | Four earlier repairs had no test guarding them, so a later change could silently undo them; each now has one that fails if the behaviour is lost. Three further defects were found and repaired. The batch-report screen returned an internal error for every request. Asking a schedule to run immediately crashed instead of saying plainly that the scheduler is not available. A usage check on the 'sides' screen read a database column that does not exist.
Write up eight measured problems and ten open choices, each with a recommended option | SYLTHARAE-Pro | Planning | 3. Round 4: probing and measuring the running system | Completed | High | 3.0 Stage: Round 4 - probing and measuring the running system | 2026-10-24 | 2026-10-24 | The work had reached points where a judgement call was needed that the engineer was not entitled to make alone, so the choices were written out instead of assumed. Eight problems came from measurement: a batch import that claims success for files it dropped; imports that vanish when the program restarts; import time that grows too fast; slow database queries; a health check that hangs during an outage; an outage that silently signs users out; and a filter that cannot be indexed at scale. Ten further choices concerned tests and documentation. Each entry states the evidence, a recommended default, and what choosing differently would cost. Nothing was changed while the owner decided.
4.0 Stage: Round 5 - carrying out the approved repairs | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | High | - (top-level task) | 2026-10-24 | 2026-10-24 | Stage in which the owner's answers were turned into repairs, plus one extra defect found on the way. Each item was shown failing first and passing afterwards, so no repair rests on a promise.
Stop a batch import from claiming success for files it silently dropped | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | High | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | A person submitting thirty files was told thirty had been accepted, while only five were actually being processed and twenty-five were silently discarded because the system allows five imports at a time. Every submitted file is now accounted for: each one ends up queued or deferred, and the totals always add up - accepted equals queued plus deferred, and accepted plus rejected equals total. A file that cannot start immediately is reported as deferred so the person knows to submit it again, instead of losing it without a trace.
Make the health check answer immediately during a database outage | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | High | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | When the database was unreachable, the health check waited out a thirty-second connection timeout and then told whoever asked the name of the internal database driver class - information that helps an attacker and no operator. It now answers within a fixed short deadline, and the answer no longer names internal software. The first attempt did not fully solve it; a second pass found the real cause, which was a database-backed translation layer running before the health check itself.
Tell users the truth when their session store is unreachable | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | Medium | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | During a database outage every user was signed out and told simply that they were not authenticated, which reads as a forgotten password and invites people to reset credentials that were never the problem. The answer now says that authentication is temporarily unavailable, gives a reason, and tells the browser how long to wait before trying again. A user whose session really was deleted still receives the ordinary not-authenticated answer, so the two situations can still be told apart.
Make the time an import takes grow in proportion to the size of the document | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | High | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | Importing a document took more than three times as long each time the file doubled in size: a four-megabyte file took five minutes, and an eight-megabyte file produced nothing within five minutes before giving up. Profiling showed two places where every item was compared against every other item. Both were rewritten to sweep through the data once, and the timings before and after were recorded so the improvement can be checked rather than believed.
Record that imports do not survive a restart, and why that was not changed | SYLTHARAE-Pro | Documentation | 4. Round 5: carrying out the approved repairs | Completed | Medium | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | A restart or crash loses every import that was queued or running: nothing resumes them, and no record survives to say they ever existed. Making them durable would require a new database table, which the agreed rules for this phase forbid. Rather than change it quietly, the behaviour was written down for users: imports run inside the web process, at most five at a time, and a second worker would keep a completely separate queue that nobody can see from the first. Making imports durable is recorded as a proposal for a later phase.
Point the failing tests at the real database instead of renaming the database | SYLTHARAE-Pro | Testing | 4. Round 5: carrying out the approved repairs | Completed | High | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | Seventeen failing tests demanded database constraint names, columns and migration numbers that this project does not have and never did. Renaming the database to match would have broken every existing installation, to satisfy names that no working code reads. The tests were corrected instead: they now assert the rule rather than the name - for example by reading the actual definition of a constraint - and they use the chain of database changes that really exists. Each rewrite kept the behaviour being asserted, and each was shown failing first and passing afterwards.
Ship the missing provenance file for the bundled place-name data | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | Medium | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | The bundled list of place names could not be packaged because the file explaining where the data comes from was missing, so the data would have shipped with no traceable origin. The provenance file was written with facts the packaging step can check, so the data now carries its source with it. A deeper redesign of how places are stored and matched was deliberately set aside for a later decision rather than half-done here.
State the software licence plainly, using only facts the project can verify | SYLTHARAE-Pro | Documentation | 4. Round 5: carrying out the approved repairs | Completed | Medium | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | The project's own configuration already declared its licence - the GNU Affero General Public License, version 3 or later - but the front page did not state it, did not explain the obligation that comes with letting people use the software over a network, and did not mention the source-code link every page must offer. All three are now stated using facts the project can check. No licence text was invented, and third-party packages whose licence metadata is unclear are listed as unclear rather than assumed acceptable.
Record five duplicate database indexes instead of dropping them | SYLTHARAE-Pro | Documentation | 4. Round 5: carrying out the approved repairs | Completed | Low | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | Five index definitions duplicate work another index already does, which costs disk space and slows down every write. Removing them is a change to the database structure and was outside the agreed rules for this phase, so each duplicate was written down with the surviving twin identified beside it. The decision to drop them stays with the owner, because dropping the wrong one would slow a query nobody is watching.
Fix a date filter that checked the wrong end of its own time window | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Completed | High | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | Notifications about a date that is about to arrive were being filtered against the wrong date column: the end of the time window was compared where the reference date belongs, so a warning about something due soon could be wrongly included or wrongly left out. The comparison was corrected, and a test that fails on the old code and passes on the new one now pins it. The defect was found while fixing the import performance problem, not by the test suite - which is exactly why the suite cannot be the only evidence.
Classify every failing test so that no failure is left unexplained | SYLTHARAE-Pro | Testing | 4. Round 5: carrying out the approved repairs | Completed | High | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | Every test that failed in this round was placed in exactly one category with a written reason: a real product defect, a test that had to be corrected because it described something untrue, something that cannot run in this environment, or something waiting on a decision from the owner. No failure was left unclassified. The principle is simple: an unexplained red test is not evidence of anything, and a suite that is allowed to stay red silently stops being a warning system.
Remove one machine's private file paths from shared reports | SYLTHARAE-Pro | Testing | 4. Round 5: carrying out the approved repairs | Completed | Low | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | 2026-10-24 | Reports produced on the working machine contained that machine's absolute folder paths, which broke an existing check that exists to stop private paths and internal hostnames leaking into shared material. The reports were rewritten to describe locations relatively, so they can be shared without disclosing how the machine is laid out.
Build the missing reporting module that two tools expect - stopped when there was nothing to build on | SYLTHARAE-Pro | Development | 4. Round 5: carrying out the approved repairs | Open | Medium | 4.0 Stage: Round 5 - carrying out the approved repairs | 2026-10-24 | Unverified | Two maintenance tools start by loading a reporting module that has never existed in this project's history, so both fail immediately. The plan of record said to build it as a thin wrapper around existing reporting code. On inspection there was nothing to wrap: the keyword-significance dataset, the report catalogue and the run engine the wrapper is supposed to expose do not exist anywhere. Writing them would mean inventing analytical SQL and then certifying it with our own assertion, which is precisely the kind of self-satisfying evidence this engagement exists to avoid. Work stopped and the decision went to the owner. Both tools still fail today; the two tests that referred to the module were later retired from the plan.
5.0 Stage: Round 6 - bringing the repaired parts together | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | High | - (top-level task) | 2026-10-24 | 2026-10-24 | Stage covering a long consolidation batch in which each subsystem was brought to one consistent rule, followed by a single complete test run kept as the reference point of record, the delivery of a translation feature end to end, and the recovery of work that a machine reset had dropped from the branch history.
Make the health and readiness checks report only what they have actually measured | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | The screens that tell an operator whether the system is healthy asserted success in places where nothing had been checked - the worst kind of green light, because it looks like assurance. They now report what was measured, how it was measured and how fresh the answer is, so 'healthy' means a check actually ran rather than a check was skipped.
Give alerts one rule for who may see them, one unread count and one display form | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | A user's unread count could disagree with the list it summarises, because the count and the list were built by different rules. Visibility, counting and the text shown in the list now all come from one rule, so the number on the screen always matches the number of items the same screen will show. The same problem also caused alerts to display a label that did not match their stored text, which is fixed by the same change.
Make background-job records readable after the fact, and their reporting honest | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | High | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Job progress used to live only in the memory of the process that ran it, so once that process was gone there was no record of what had happened or why. Progress is now recorded in a form that can be read back later. The import accounting repaired earlier is applied the same way on every import path, so two screens can no longer report different totals for the same set of files.
Make one definition drive the scenario rules, the screen and the database query | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | A scenario was described once for the rules engine, again for the screen, and a third time for the query builder, so the three could drift apart and silently disagree - the analyst seeing one thing while the engine evaluated another. They now share a single definition, so what is displayed, what is evaluated and what the database is asked cannot diverge.
Rewrite overlap detection to sweep the data once, and keep evidence provenance intact | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Detectors were merging overlapping matches by comparing every match against every other match, which becomes unusable on long documents; that was replaced with a single ordered sweep. Two related gaps were closed at the same time: the kind of an identifier is now carried inside its evidence rather than only in a type name that can be renamed, and place data carries its source with it so a result can be traced back to the list it came from.
Build the reporting behaviour on the existing reporting services, with no database change | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | The reporting capability described in the plan was implemented on top of the reporting services that already exist: what was missing was the reporting logic, not new tables. This is deliberately not the module that the two maintenance tools expect, which remains unbuilt and open; the two are different things and are recorded separately so that one cannot be mistaken for the other.
Check every database read behind the places and saved-search screens against the real database | SYLTHARAE-Pro | Verification | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Every read used by the places screens and the saved-search screens was compared statement by statement against the database that actually exists, so a query referring to a column that is not there could not survive to the moment a user clicks. The mismatches found were corrected rather than documented.
Apply the same access checks to the authentication, export and translation addresses | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Some web addresses checked who was calling, some checked what that caller was allowed to do, and some checked neither. Sign-in, permissions, forged-request protection and export rights were made uniform across these three areas, so no address is protected merely by being hard to guess. Uniformity matters more than the individual checks: a gap in one family is invisible until someone finds it.
Record every installed package, its licence, and whether that licence is compatible | SYLTHARAE-Pro | Research | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | One hundred and sixteen installed packages were recorded with the version and licence each declares, alongside a verdict on whether that licence is compatible with releasing this software under the GNU Affero GPL. A generated notice file lists the third-party components that ship with the product. Packages whose licence metadata is unclear are listed as unclear, not assumed harmless, because an unclear licence is a legal risk and not a clerical detail.
Write down the data-retention rules and the index definitions readiness depends on | SYLTHARAE-Pro | Documentation | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Two questions operators kept asking had no written answer: how long data is kept, and which database indexes the readiness check relies on. Both are now written down, so a readiness result can be defended instead of inferred, and so that a future change to either can be recognised as a change rather than discovered by accident.
Bring every audit report, inventory and finding into one committed record | SYLTHARAE-Pro | Documentation | 5. Round 6: bringing the repaired parts together | Completed | High | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | The reports, the twelve complete inventories and the findings lists had been produced over several days and were scattered across a working machine that is wiped between sessions. They were committed together with the raw evidence each one rests on, so that anyone picking this up later - including the owner - can trace a claim back to the run that produced it. Without that, every number in this register would be an assertion.
5.1 Sub-stage: the translation feature | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | High | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Sub-stage inside the consolidation round: a translation feature delivered end to end in a single afternoon - engines, memory, web interface, screen and placement in the reading flow. Three design decisions governed it: the stored original text is never modified; the translation memory lives in a local file rather than in the frozen database; and every machine translation is labelled as unverified so it can never be mistaken for a checked one.
Choose translation engines so that no restrictive licence is quietly relied on | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | The translation feature defaults to an engine with permissive licensing. A higher-quality neural engine is available only as an option and is flagged as non-commercial, so a deployment cannot drift into depending on it without noticing. If an engine cannot fetch the model it needs, the user is told why rather than receiving a generic failure that suggests the software is broken.
Make translation read stored text only, with no path that can alter it | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | The translation service can only read text the system has already stored; it has no path that modifies, replaces or overwrites the original. That constraint is built into the service rather than left to each caller to respect, so a bug or a rushed change elsewhere cannot corrupt source material that may be the only copy of an intercepted document.
Split sentences, detect the language, and remember what has already been translated | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | High | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | Long passages are split into sentences so they can be translated and compared in readable pieces, the language is detected rather than assumed from a setting, and every completed translation is remembered. Repeating the same passage therefore costs nothing and returns the identical wording, which is what makes a translation reproducible. The memory is a local file outside the database, so the frozen database structure is untouched.
Decide who may correct a translation, what a correction outranks, and what is recorded | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | Only permitted roles may correct a translation. A human correction always outranks a machine result and is never overwritten by a later machine run, so a translator's work cannot be quietly lost. Each stored entry records who produced it, when, and whether it was machine or human. Those three rules are enforced in one place, so every route that touches the memory obeys the same rules.
Accept translation requests only by form submission, with forgery protection, limits and an audit record | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | Translation requests are accepted only as deliberate form submissions, require the same anti-forgery token as every other action that changes state, enforce length limits, validate their input, and write an audit record naming who asked for what. The result is that translation cannot be triggered by a link, an image or a page on another site, and cannot be used to burn through a third-party engine's quota anonymously.
Let the reader compare, accept or correct a translation, always labelled as unverified | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | The reader selects text, sees the translation beside the original, and can accept it in one click or correct it in place. Machine output is labelled as unverified so it can never be mistaken for a checked translation, which matters on legal and intelligence material. Accepting is deliberately cheaper than correcting, so the common case stays fast while the careful case remains available.
Report translation failures as service-unavailable with a reason, never as a crash | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | High | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | Two failure paths were returning a generic internal error: a translation memory file that could not be read, and an engine that could not download its model. Both now answer that the service is temporarily unavailable, with the reason, which tells an operator what to fix. A memory file that cannot be read is never silently treated as empty, because an empty memory would retranslate everything and quietly discard human corrections.
Put the translation panel where the reader already is | SYLTHARAE-Pro | Development | 5. Round 6: bringing the repaired parts together | Completed | Low | 5.1 Sub-stage: the translation feature | 2026-10-24 | 2026-10-24 | The translation control existed but could only be reached through a separate address, so in practice nobody would find it. It now appears in the reading flow, next to the text it acts on, which is the only placement that makes a translation feature usable.
Re-run the hostile-input and route probes after the new translation addresses were added | SYLTHARAE-Pro | Testing | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | Nine new web addresses had been added, so the earlier sweeps no longer covered the whole surface and their clean result had stopped meaning anything. Both sweeps were re-run against everything, with the same test data and settings as before, so the comparison is like for like and the clean result covers the new code as well as the old.
Keep one complete test run, with a browser walk of every screen, as the reference point | SYLTHARAE-Pro | Verification | 5. Round 6: bringing the repaired parts together | Completed | High | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | A single complete run was recorded so that later rounds could be compared against something stable: 4,399 tests with 51 failures, 11 errors and 14 skips, plus a real browser walk of every screen saved with screenshots. Every failing test was then given a category - thirty-eight needed documents that are deliberately not published, twenty-four were waiting on decisions, and none was an unexplained product defect. The last number is the one that matters: it said the remaining red was bureaucratic, not dangerous.
Rejoin the work that a machine reset had dropped from the branch | SYLTHARAE-Pro | Coordination | 5. Round 6: bringing the repaired parts together | Completed | Medium | 5.0 Stage: Round 6 - bringing the repaired parts together | 2026-10-24 | 2026-10-24 | The working machine had been wiped and the branch rebuilt from scratch, so work that existed only on the remote copy - two whole rounds of earlier repairs - was no longer in the branch's history and could have been silently lost or duplicated. It was merged back in, so the record is complete and no repair exists twice in two slightly different forms.
6.0 Stage: Round 10 - better tests, honest failure handling, runbook | SYLTHARAE-Pro | Development | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | - (top-level task) | 2026-10-25 | 2026-10-25 | Stage covering the round that corrected the tests themselves, made three failure paths honest, hardened installation, broke the system on purpose to see how it behaves, measured speed at full scale, and produced the operator runbook.
Correct five groups of tests without weakening a single assertion | SYLTHARAE-Pro | Testing | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | Five groups of tests asserted things that are simply not true of this database: a column that does not exist, index names that differ, and migration numbers belonging to another project. They were rewritten against what actually exists while keeping the same behaviours under test - six, eight, twenty-two and twelve tests respectively, plus all the volume guards. In the index case the test now checks the columns and their order, which is what actually determines speed, instead of a name that determines nothing. Each group was shown failing before the rewrite and passing after it.
Handle a full disk, an unreadable memory file and stale job records honestly | SYLTHARAE-Pro | Development | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | Three failure paths were either dishonest or missing. A full upload volume returned a generic server error instead of saying storage is exhausted. An unreadable translation memory returned an internal error instead of saying the memory is unavailable. Jobs left marked as running by a killed process stayed running for ever, so the queue silently looked busy when it was empty. All three now report the true condition, and stale running jobs are cleared the next time the software starts.
Check index columns rather than index names, and pin the identifier record type | SYLTHARAE-Pro | Testing | 6. Round 10: better tests, honest failure handling, runbook | Completed | Medium | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | One test asserted the names of database indexes, which proves nothing about speed - two indexes can have the same name and different columns, or the reverse. It now reads the database's own description of each index and asserts its columns in order. A second test now pins the record type the identifier detector must produce, so a rename cannot silently break every filter that depends on it.
Make installation fail loudly and clearly on a clean machine | SYLTHARAE-Pro | Development | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | Several installation paths failed quietly. A database with the wrong text encoding was accepted and would misbehave later. An installation could finish without ever creating the administrator account needed to use the system, leaving a product nobody could sign in to. The command-line installer did not work at all on a clean copy of the project. Each path now refuses to continue and says why. In addition the scheduler's one required package is declared, a system-settings address is readable by every signed-in role, a place note is refused rather than silently dropped, and one test was made independent of the rest of the suite so it cannot fail because of test order.
Prove how the system behaves by breaking it on purpose | SYLTHARAE-Pro | Testing | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | Failure was injected deliberately rather than imagined: an upload volume with only eight megabytes free, the database stopped in the middle of an import, the web process killed outright, and the application restarted mid-job. Each run recorded what the user was told and what survived. This is behaviour, not a statistical guarantee - each drill was run once, on a small machine - and it is recorded that way, so nobody mistakes three successful drills for resilience under load.
Measure speed at 100,000 records, walk every screen in three right-to-left languages, and sweep for security gaps | SYLTHARAE-Pro | Measurement | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | Speed was measured against a realistic hundred-thousand-record database. Every screen was then loaded and operated in a real browser at three screen widths in Arabic, Hebrew and Farsi, because a right-to-left layout breaks differently from a left-to-right one and nobody had ever looked. Security sweeps were run across the same surface. Every result was recorded, and each failure was either repaired or listed as open - nothing was quietly dropped because it was inconvenient.
Build a benchmark for translation speed and memory, and be explicit that it is not a quality test | SYLTHARAE-Pro | Tooling | 6. Round 10: better tests, honest failure handling, runbook | Completed | Medium | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | A small tool measures how long translation takes and how much memory it uses, and writes the result in a form a spreadsheet can read. It has only ever been run against a placeholder engine, because the real translation engine is not installed on the machine, so its figures describe the harness and not the engine. Nothing about translation quality has been measured at any point, and the tool says so rather than presenting a number that would be misread as a model benchmark.
Write the operator runbook: install, upgrade, backup, restore, health and logs | SYLTHARAE-Pro | Documentation | 6. Round 10: better tests, honest failure handling, runbook | Completed | High | 6.0 Stage: Round 10 - better tests, honest failure handling, runbook | 2026-10-25 | 2026-10-25 | An operator with a working database now has a step-by-step procedure for installing the software, upgrading it, taking a backup, restoring that backup, checking health and reading logs. The section on failure behaviour states only what was actually measured, and the runbook also says plainly what it cannot tell you - restoring into a different database version, for instance, has never been tried.
7.0 Stage: Round 11 - a real category hierarchy and its screen | SYLTHARAE-Pro | Development | 7. Round 11: a real category hierarchy and its screen | Completed | High | - (top-level task) | 2026-10-25 | 2026-10-25 | Stage covering the round that made a real category hierarchy possible for the first time, delivered the web interfaces behind it, measured the tree at scale before designing the screen, and built that screen with list and map views.
Replace the rule that limited categories to two levels with a guard against loops | SYLTHARAE-Pro | Development | 7. Round 11: a real category hierarchy and its screen | Completed | High | 7.0 Stage: Round 11 - a real category hierarchy and its screen | 2026-10-25 | 2026-10-25 | The database enforced a 'two levels only' rule with a trigger, which made any deeper category structure impossible - a real limitation for anyone organising a large collection. A new database change replaces that trigger with a guard that permits any depth while refusing a loop: a category cannot become its own ancestor, directly or through any chain. This is the only database change made in the whole engagement, it is reversible, and its reversal and re-application were both exercised on a database that already contained data.
Add the web interfaces needed to browse, adopt, move and delete categories in a tree | SYLTHARAE-Pro | Development | 7. Round 11: a real category hierarchy and its screen | Completed | High | 7.0 Stage: Round 11 - a real category hierarchy and its screen | 2026-10-25 | 2026-10-25 | New addresses return categories level by level with their depth, insert a new category above an existing one, move a category while refusing any move that would create a loop, and delete with the necessary checks. Loop refusal is enforced by the database itself, so no caller - a screen, a script or a future integration - can bypass it by accident.
Measure the category tree at 10,000 and 100,000 categories before building the screen | SYLTHARAE-Pro | Measurement | 7. Round 11: a real category hierarchy and its screen | Completed | Medium | 7.0 Stage: Round 11 - a real category hierarchy and its screen | 2026-10-25 | 2026-10-25 | The screen was designed after measuring rather than before. The tree was loaded at ten thousand and at a hundred thousand categories and timed, and the numbers showed that returning the whole tree in one answer would not work at the larger size. That single measurement decided the shape of everything that followed: levels had to be fetched on demand.
Build the category hierarchy screen with list and map views | SYLTHARAE-Pro | Development | 7. Round 11: a real category hierarchy and its screen | Completed | High | 7.0 Stage: Round 11 - a real category hierarchy and its screen | 2026-10-25 | 2026-10-25 | A new screen shows categories as a tree in a list and on a map, lets a person choose a parent when creating a category, drag a category onto another to move it, operate the whole thing from the keyboard, and export the tree as a file for a spreadsheet. Loop prevention and permission checks apply to every route into the data, not only to the buttons on the screen.
Drive the new category screens in a real browser and record what happened | SYLTHARAE-Pro | Verification | 7. Round 11: a real category hierarchy and its screen | Completed | High | 7.0 Stage: Round 11 - a real category hierarchy and its screen | 2026-10-25 | 2026-10-25 | The new screens were operated in a real browser rather than assumed to work: creating a category, moving one under another, navigating by keyboard and exporting the tree were each performed, and the outcome of each was recorded together with the request it produced. Automated tests can pass while a screen is unusable; only a browser catches that.
Write the operator and developer documentation and put it up for human review | SYLTHARAE-Pro | Documentation | 7. Round 11: a real category hierarchy and its screen | Pending Review | Medium | 7.0 Stage: Round 11 - a real category hierarchy and its screen | 2026-10-25 | 2026-10-25 | Three documents were written for people rather than for tests: how to configure a deployment, how to work on the code itself, and what the security model protects and what it does not. They are finished and committed, but no human has read them yet, so they are held as pending review and treated as unapproved. A document nobody has read is not evidence, and publishing one as though it were would repeat the original problem of documentation drifting away from reality.
8.0 Stage: Round 12 - repairing broken screens and the tree | SYLTHARAE-Pro | Development | 8. Round 12: repairing broken screens and making the tree efficient | Completed | High | - (top-level task) | 2026-10-25 | 2026-10-25 | Stage covering the round that repaired screens which had stopped rendering, replaced the whole-tree request with on-demand levels, brought the published list of web addresses back in line with reality, and proved the new database change can be undone.
Regenerate the list of every published web address by machine instead of by hand | SYLTHARAE-Pro | Verification | 8. Round 12: repairing broken screens and making the tree efficient | Completed | Medium | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | The published list of web addresses had been edited by hand and had drifted from what the software actually offers. It is now produced by a script that asks the running application itself, so it cannot be wrong: 501 addresses, including the three new category-tree addresses, and no addresses that exist only while tests are running. A hand-maintained list of interfaces is a liability; a generated one is evidence.
Fetch category levels on demand so that one screenful costs one level, not the whole tree | SYLTHARAE-Pro | Development | 8. Round 12: repairing broken screens and making the tree efficient | Completed | High | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | Returning an entire category tree in one answer is fine for a few hundred categories and hopeless for a hundred thousand - the browser would stall and the server would spend its effort serialising data nobody is looking at. Three addresses now return only the roots, only one level's children, and the counts. Opening a page now costs one level of work regardless of how large the tree is.
Repair the category list screen and make the parent selectors correct and immediate | SYLTHARAE-Pro | Development | 8. Round 12: repairing broken screens and making the tree efficient | Completed | High | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | The category list screen had stopped rendering at all, and its parent column could not name a parent whose row happened to sit on another page, so a hierarchy looked flat whenever it spanned a page boundary. Both are fixed: the screen renders again, and parents are named correctly even when they are on a different page. The parent selector also paints immediately with what is already known instead of showing an empty box until a request returns, which made people think it had nothing to offer.
Give the route sweeps real category identifiers and re-run them | SYLTHARAE-Pro | Testing | 8. Round 12: repairing broken screens and making the tree efficient | Completed | Medium | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | The parameterised sweeps had been sending the literal text of a placeholder where a real identifier belongs, so they were proving only that the software rejects nonsense - impressive-looking and worthless. Real identifiers were supplied from a live database and all three sweeps were re-run. Their clean result now means something, because the requests were real.
Assert the current database revision and prove the new category change can be undone | SYLTHARAE-Pro | Testing | 8. Round 12: repairing broken screens and making the tree efficient | Completed | High | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | Two test fixtures insisted the newest database revision was number three, so the fourth change broke sixteen tests the moment it landed. They now assert whatever the current revision actually is, so the next change will not break them. The new database change was then applied, undone and re-applied on a database that already held data, which is the only case that matters: an empty database proves almost nothing about a migration.
Regenerate the database description so it describes the database that exists | SYLTHARAE-Pro | Documentation | 8. Round 12: repairing broken screens and making the tree efficient | Completed | Medium | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | The published description of the database became wrong the moment the category rule changed. It was regenerated from the chain of changes that actually builds the database, so the description cannot disagree with the code. This is the difference between documentation that is generated and documentation that is remembered.
Keep test-only addresses out of the published list, and stop the browser's cache being committed | SYLTHARAE-Pro | Tooling | 8. Round 12: repairing broken screens and making the tree efficient | Completed | Low | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | The address generator had started recording addresses that exist only while tests are running, which would have made the published list describe something no deployment has. It now excludes them. The browser used for testing writes a cache folder into the project directory; that folder is now ignored so it cannot be committed by accident and cannot make an unrelated file look changed.
Re-run the full test suite on a clean copy and compare it with the previous round | SYLTHARAE-Pro | Verification | 8. Round 12: repairing broken screens and making the tree efficient | Completed | High | 8.0 Stage: Round 12 - repairing broken screens and the tree | 2026-10-25 | 2026-10-25 | Two complete runs were made on fresh copies of the project with fresh databases: 67 failing unit tests and 7 failing integration tests, exactly the same identifiers as the previous round, and not one new failure introduced. Twelve unit tests and one integration test that had failed before now pass. The same numbers twice, from a clean copy rather than a used one, is what makes them worth quoting.
9.0 Stage: Round 13 - fixing the two defects people hit | SYLTHARAE-Pro | Development | 9. Round 13: fixing the two defects a person would actually hit | Completed | High | - (top-level task) | 2026-10-25 | 2026-10-25 | Stage covering the round that fixed two defects a real person would hit within minutes of using the software, and recorded the state of the test suite after the fixes.
Repair the Add-category dialog on the category list screen | SYLTHARAE-Pro | Development | 9. Round 13: fixing the two defects a person would actually hit | Completed | High | 9.0 Stage: Round 13 - fixing the two defects people hit | 2026-10-25 | 2026-10-25 | Creating a category from the list screen's dialog could not be completed at all: a check on the chosen parent rejected valid choices, so the save never happened and the person was left with a form that did nothing. The check was corrected, and creating a category from that screen was then performed in a real browser and confirmed to produce the category. This defect existed despite the surrounding screens being tested, which is why browser work is part of the method.
Stop the software behaving differently depending on which folder it is started from | SYLTHARAE-Pro | Development | 9. Round 13: fixing the two defects a person would actually hit | Completed | Medium | 9.0 Stage: Round 13 - fixing the two defects people hit | 2026-10-25 | 2026-10-25 | A marker file that tells the software it has been installed was being looked up relative to whatever folder the process happened to start in. Started from a different folder, the application could behave as though it had never been installed, or as though a fresh installation were needed. It is now resolved from the data folder, which is the same wherever the process starts - a small change that removes a whole class of confusing support reports.
Record the state of the test suite and the repaired dialog after the two fixes | SYLTHARAE-Pro | Verification | 9. Round 13: fixing the two defects a person would actually hit | Completed | High | 9.0 Stage: Round 13 - fixing the two defects people hit | 2026-10-25 | 2026-10-25 | The full suite was run again after the two repairs: the failing test identifiers were unchanged from the previous round, and the browser pass that creates a category from the list screen succeeded. Both facts are recorded so the repairs can be judged against the state that existed before them, rather than against a reassuring recollection.
10.0 Stage: Round 14 - action ownership and re-checks | SYLTHARAE-Pro | Development | 10. Round 14: one button, one action, and a re-check of the rest | Completed | High | - (top-level task) | 2026-10-25 | 2026-10-25 | Stage covering the current round: making sure each button does exactly one thing, driving the category insertion path in a real browser, finding out whether the text-recognition failures were real defects, and re-measuring the system at full scale so the numbers can be compared with the earlier run.
Give every clickable action exactly one owner on each screen | SYLTHARAE-Pro | Development | 10. Round 14: one button, one action, and a re-check of the rest | Completed | High | 10.0 Stage: Round 14 - action ownership and re-checks | 2026-10-25 | 2026-10-25 | Eight action names were defined in more than one script, so which one a button actually ran depended on the order the scripts happened to load - a fault that appears on some screens and not others, and that no amount of testing one screen would catch. Each name now has exactly one owner on each screen. A real browser then opened all eighteen affected screens, clicked each control and recorded which request or effect each click produced: seventy checks with no unexpected result. Eight remaining differences were classified, four as real defects on two screens and four as gaps in the test data rather than in the product.
Prove in a browser that a new category can be inserted above an existing one | SYLTHARAE-Pro | Verification | 10. Round 14: one button, one action, and a re-check of the rest | Completed | High | 10.0 Stage: Round 14 - action ownership and re-checks | 2026-10-25 | 2026-10-25 | The 'adopt' path - inserting a new parent above a category that already exists - had only ever been exercised by script, which proves the interface works but not that the screen can reach it. It was performed through the screens in a real browser: all ten checks passed, the request returned a created result, and the new parent correctly reported its two children. This closes a gap that an earlier round had explicitly listed as unverified.
Find out whether the text-recognition failures were real defects, and repair the actual cause | SYLTHARAE-Pro | Verification | 10. Round 14: one button, one action, and a re-check of the rest | Completed | High | 10.0 Stage: Round 14 - action ownership and re-checks | 2026-10-25 | 2026-10-25 | Thirty-one tests about reading text out of images and scanned pages were failing, which looked like a broken feature. The cause was the machine, not the product: it had no text-recognition engine installed, and the image library the alternative engine needs was the wrong build. With the correct library installed, the eight affected test files gave 188 tests with two failures and no errors. Every remaining failure was then explained individually: twenty-nine were the missing engine, two need a document that is deliberately not written yet, and none was a defect in the text-recognition code itself. The value here is the classification - thirty-one scary red tests became zero defects and two known gaps.
Re-measure at 100,000 records and compare the result with the earlier run | SYLTHARAE-Pro | Measurement | 10. Round 14: one button, one action, and a re-check of the rest | Completed | Medium | 10.0 Stage: Round 14 - action ownership and re-checks | 2026-10-25 | 2026-10-25 | The hundred-thousand-record database was rebuilt in twenty-nine seconds, thirty-three requests were served, and they issued two hundred and sixty database statements in total. The last page of five hundred results took twenty-one milliseconds against twelve for the first, the heaviest management screens took a quarter of a second, an identifier filter took under a tenth of a second, and no screen issued a separate query per row. The earlier run is shown beside the new one, because a performance number on its own means nothing.
Put the whole repair branch up for review instead of merging it | SYLTHARAE-Pro | Coordination | 10. Round 14: one button, one action, and a re-check of the rest | Pending Review | High | 10.0 Stage: Round 14 - action ownership and re-checks | 2026-10-25 | Unverified | All the work sits on a separate branch and has been opened for review rather than merged. The change is large, it touches behaviour a person can see, and the main line must stay untouched until someone has looked at it. Review is the current state: nothing has been merged, nothing is promised for a particular day, and the owner decides whether it goes in, waits, or is revised.
11.0 Stage: open work carried forward | SYLTHARAE-Pro | Planning | 11. Open work: unfinished, blocked or never attempted | Working | High | - (top-level task) | 2026-10-25 | Unverified | Stage holding everything that is unfinished, blocked on a decision, or was never attempted. Each entry states what is missing and why, in plain terms, and no entry claims a completion date that nobody has evidence for. Nothing here is a guess about what somebody intended: each line describes a gap that can be seen in the software as it stands.
Finish the full test comparison on a clean copy of the review branch | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Working | High | 11.0 Stage: open work carried forward | 2026-10-25 | Unverified | A clean copy of the branch was made and the unit half of the test suite has finished: 3,268 tests, of which 3,218 passed, 28 failed, 11 could not start and 11 were skipped - thirty-nine failing identifiers. Compared with the previous round, twenty-nine identifiers now pass, all of them text-recognition tests that had been failing only because the engine was missing, and one is newly failing. The integration half was started but had not finished, so there is still no complete two-part figure for the current state of the branch. Until there is, the newest numbers in this register are the unit half only.
Repair the test broken by this round's action renaming | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Urgent | 11.0 Stage: open work carried forward | 2026-10-25 | Unverified | One test is newly failing because of this round's own work. It insists on a specific line of code that published a select-all action under an old name, and that line was replaced when action names were given single owners. One of the two must give way: either the control keeps publishing under the old name, or the test checks the behaviour - that the name resolves and that clicking it selects - instead of the text of an assignment. This is the only failure the round introduced, and it is marked urgent because it belongs in the review that is waiting for the owner, not in a later round.
Write the four written references that have never existed | SYLTHARAE-Pro | Documentation | 11. Open work: unfinished, blocked or never attempted | Open | Medium | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Several checks expect four written references: a register of every interface the software offers, the evidence behind that register, a map of which parts are genuinely product-ready, and a description of the subject matter the software models. None of the four has ever existed, so eleven interface checks and two text-recognition checks cannot pass, and thirteen failures are waiting on a decision rather than on code. Writing them was deliberately not done to turn tests green, because a document written only to satisfy a test is the same drift the whole engagement is fighting.
Translate the 562 untranslated phrases into the four supported languages | SYLTHARAE-Pro | Documentation | 11. Open work: unfinished, blocked or never attempted | Open | Medium | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Five hundred and sixty-two phrases that appear in the interface have no translation into Arabic, Hebrew, Farsi or Croatian, and the checks that insist no entry is empty or marked uncertain still fail for all four languages. Machine translation was refused deliberately: a wrong translation on a legal or intelligence screen is worse than an untranslated phrase, because the reader cannot tell that it is wrong. This waits for a human translator, and no date is given because the translator's availability is not something this project can see.
Start the scheduler that is declared but has never run | SYLTHARAE-Pro | Development | 11. Open work: unfinished, blocked or never attempted | Open | Medium | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | The software declares a scheduler for time-based work, but at every start it fails to load, and nothing scheduled has ever run - the same error appears in every server log. Wiring it up was explicitly out of scope until the owner answers three open questions, so no scheduled task has ever been verified as working. It stays listed because an unreachable feature that looks present is worse than a missing one.
Fix the bulk-delete button on the keywords and words screens | SYLTHARAE-Pro | Development | 11. Open work: unfinished, blocked or never attempted | Open | Medium | 11.0 Stage: open work carried forward | 2026-10-25 | Unverified | On two screens the bulk-delete control never becomes usable: the shared action bar switches the button off and never restores the instruction that tells it what to run, so no delete request is ever sent. Four automated browser checks on those two screens record that the request is never issued. The cause is identified precisely; the repair has not been written, and nothing is claimed about it beyond the observation.
Re-run the whole text-recognition test family with an engine installed | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-25 | Unverified | Only the eight test files that directly touch text recognition were re-run once the engine was working. The rest of that family - scanned pages, images embedded inside documents, rotated pages and searchable output - still carries failures recorded before the engine was fixed. Their present state is therefore unknown rather than passing, and saying otherwise would be exactly the kind of inherited claim this engagement exists to eliminate.
Lift the 500-category limit in the list screen's parent selector | SYLTHARAE-Pro | Development | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-25 | Unverified | The parent selector on the category list screen asks for at most five hundred categories in a single request. Above that number a person cannot choose every possible parent, and the list silently stops being complete - the failure mode where the missing options look like options that do not exist. The tree screens already handle this correctly by fetching levels on demand; the list screen has not been converted.
Build and install the offline package on a Windows machine | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | There is an offline installation kit for machines with no internet access, and a check that its list of required packages matches what is actually installed. Parts of that check fail, and the kit itself has never been built, installed or used on Windows, because no Windows machine was available. Nothing about the offline installation path has been verified, so it should be treated as written but untested.
Measure translation quality with a real engine | SYLTHARAE-Pro | Measurement | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Translation has been measured only for speed and memory, and only against a placeholder engine. Whether the translation is any good has never been measured, because the real engine is not installed. Until someone does that work, no statement about translation quality can honestly be made, and the existing timings must not be presented as if they were one.
Test the software under real concurrent load | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Medium | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Every speed figure in this register comes from one user on a small machine. There has been no multi-user soak test and no test of what happens when the database connection pool is exhausted. The software is documented as supporting exactly one process per database, and that limit itself has never been load-tested, so the safe operating envelope is an assertion rather than a measurement.
Restore a backup into a different version of the database server | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Backup and restore were tested from one version of PostgreSQL into the same version. Restoring into a newer or older major version - the situation an operator actually faces when rebuilding a server - has never been attempted. The runbook says so instead of implying that any restore will work.
Redesign how place names are stored and matched | SYLTHARAE-Pro | Planning | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Places are currently identified by a generated key that the rest of the system treats as a stopgap, and matching a place mentioned in a document against the bundled list is cruder than it should be. A proper design - typed place categories, single-word terms and multi-word phrases treated differently - was set aside by instruction, so nothing about it has been designed or tested. It is a database change, so it also needs the freeze lifted.
Exercise the 65 addresses that had no usable test data | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Of one hundred and fifty-five addresses that accept an identifier, sixty-five could not be tried because the records they need did not exist in the test database. They are recorded as untested rather than as passing, and they remain the largest single gap in coverage of the software's web surface. Closing it means building realistic test data through the application's own interfaces rather than inserting rows directly.
Make the interface-coverage check generate its evidence from a clean application | SYLTHARAE-Pro | Testing | 11. Open work: unfinished, blocked or never attempted | Open | Low | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | One check fails for a reason inside the check itself. It builds the list of published addresses during the same test session in which the security tests have registered extra addresses, so the list it compares against contains routes that no real installation has. The check should build a fresh application before generating its comparison, which would make it measure the product instead of the test session.
Build the report dataset and run engine that two maintenance tools load at start-up | SYLTHARAE-Pro | Development | 11. Open work: unfinished, blocked or never attempted | Open | Medium | 11.0 Stage: open work carried forward | 2026-10-24 | Unverified | Two maintenance tools - one for a translation report and one for measuring keyword significance - begin by loading a reporting module that does not exist, so both fail immediately. Building it means writing the analytical query for keyword significance, a catalogue of reports and a run engine: a project in its own right, not a patch, and therefore a decision for the owner rather than something to slip in. This is the same gap recorded earlier as stopped work; it is repeated here so that no reader believes it closed.

## How to Read This
HOW TO READ THIS REGISTER
What this workbook is
It is a record of work done on one software product between 23 and 25 October 2026, written so that a reader who knows nothing about software can follow it. Each task says what was wrong, what was done about it and what was checked afterwards. Nothing in it requires another file to be understood.
It is not a plan or a promise: dates are either the day the work actually happened or an amber cell saying the date is not evidenced.
The status values, and what each one means here
Completed - the work is done and was checked afterwards. Used only where a test, a measurement or an observed result exists.
Working - started and not finished. The description says exactly how far it got.
Pending Review - finished by the person who did it, but not yet read, approved or merged by someone else. It is treated as unapproved until that happens.
Open - known, described and not yet started, or stopped deliberately because a decision is needed first.
Overdue - not used. Nothing in this record has an agreed due date, so calling a task overdue would invent a commitment nobody made.
Template - not used. This register records real work rather than reusable task patterns.
Cancelled - not used. Nothing was abandoned after starting; the one task that was stopped is kept as Open for the reason given in its description.
The priority values
Urgent - must be settled before the branch under review can be accepted. Used once, for the single test this round broke.
High - the work affects whether a person can use the software, whether data can be lost, or whether a claim can be trusted.
Medium - real defects and real gaps, but with a workaround or a limited blast radius.
Low - clean-up, documentation and improvements that do not change whether the software works.
Priorities were taken from the severity already assigned when each problem was found, not assigned afresh for this workbook.
How the dates work
Every date in the two date columns falls inside October 2026, and no date is later than 25 October 2026, the day this register was produced.
A plain date is a real date: the day the work actually started or finished, taken from the project's own history.
An amber cell reading Unverified is the honest answer that no evidenced date exists. The description says what is missing and, where it can be judged, roughly how much work remains in words rather than in an invented date.
The work described here began on 23 October 2026. Nothing earlier is claimed, because the project's history contains no earlier record of work.
For a task that has never been started, the start column shows the day the gap was first recorded as known work, and the end column says Unverified because nothing has been finished and no completion has been agreed.
How the tasks are organised
The eleven numbered rows ending in '.0 Stage:' are stage headings. Each one groups the work of a single stretch of effort, and each child task names its stage in the 'Main Task (Original/Parent)' column.
The translation feature is a sub-stage inside stage 5, and its eight tasks name it as their parent, so there are three levels in that part of the register.
The 'Does it fall under a group?' column repeats the stage name on every child row so that a filtered or sorted view stays readable.
The 'Type' column uses plain words: Development, Testing, Verification, Research, Planning, Measurement, Documentation, Tooling, Setup and Coordination.
What is covered
One hundred and five rows: eleven stage headings, one sub-stage heading, ninety-three individual tasks, covering every piece of work recorded in the project between 23 and 25 October 2026 - research, planning, building, testing, measuring, documenting and coordinating.
Seventy-four individual tasks are completed, eighty-five rows in total once the finished stage headings are counted. Every completed task states the check that followed it.
Nineteen individual tasks are still open - two in progress, two awaiting review, fifteen not started - and each one states plainly what is missing and what it would take.
The register distinguishes work that changed the product from work that checked it: forty-five rows are development, forty are testing, verification or measurement, ten are documentation and the rest are planning, setup, tooling or coordination.
What is not covered, and why
Anything before 23 October 2026. The software is older than this record, but its history was captured in a single step with no dates, so no earlier work can be dated without inventing it.
Anything after 25 October 2026. No future commitment is recorded, and no open task has a promised completion date.
Work that left no trace. Three early rounds were lost when the working machine was wiped and had to be rebuilt; the repairs survived, but their individual dates did not always do so.
The two documents that describe how to run and develop the software have been written but not read by a human, so they appear as pending review rather than as completed documentation.
Four written references, the translations into four languages, the scheduled-work feature and the scaled tests are genuinely unfinished. They are listed as open rather than quietly omitted.