## Tasks
Subject or Tasks | Project | Type | Is it a group? | Status | Priority | Parent Task | Expected Start Date | Expected End Date | Details | Task Description
SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | SYLTHARAE file analysis | Project | Yes | In progress | High |  | 2026-10-01 | 2026-10-10 | All dates in America/Adak. Parent effort covering map viewer, exports, localization, and QA. | Complete file-analysis interfaces: geolocation/map, export/download paths, ar/he/fa/hr UI, analyst categorization, CI and browser sign-off.
Map Viewer — page, layers, geotagged markers, MapLibre integration | SYLTHARAE file analysis | Feature | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-01 | 2026-10-04 | Completed 2026-10-04 (America/Adak). templates/map/map_viewer.html, map-viewer-page.js, map_api, marker icons by file type. | Ship interactive map viewer with layered basemaps and file markers.
Offline map tile cache (WebP in map_data/registry.db) + cache proxy API | SYLTHARAE file analysis | Feature | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-02 | 2026-10-04 | Completed 2026-10-04 (America/Adak). services/map_tile_cache.py, GET /api/map/cache/, auto-cache preference. | Persist viewed tiles locally for offline map use.
Portable map bundle (.sylmap.tar.gz) export/import | SYLTHARAE file analysis | Feature | No | Completed | Medium | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-03 | 2026-10-04 | Completed 2026-10-04 (America/Adak). services/map_bundle.py, map_registry SQLite, UI import/export. | Move map data between devices via portable archive.
Geolocation export API + FMAS map/export chrome | SYLTHARAE file analysis | Feature | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-03 | 2026-10-04 | Completed 2026-10-04 (America/Adak). exports.py geolocation, section-export-menu.js, archives alias. | Export and open geolocation from file analysis surfaces.
UI fixes — stuck cursor, modal/FMAS/bulk action buttons | SYLTHARAE file analysis | Bug fix | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-04 | 2026-10-04 | Completed 2026-10-04 (America/Adak). fmas.css pointer-events, event-delegation.js, file-view.js tooltips. | Restore clickable controls and normal cursor on action bars.
Export/download QA — smoke script + interface registry tests | SYLTHARAE file analysis | QA | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-04 | 2026-10-05 | Completed 2026-10-05 (America/Adak). export_surfaces_smoke.py, test_export_interface_registry.py; live GET exports 200 OK. | Verify all major export/download endpoints and registry coverage.
Soft navigation / initializer idempotency audit | SYLTHARAE file analysis | Technical debt | No | Completed | Medium | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-04 | 2026-10-05 | Completed 2026-10-05 (America/Adak). Navigation swap, FunctionManager, FMAS/files-list/search hardening. | Prevent double-init and stale handlers on soft navigation.
Map Viewer + navigation registry i18n (ar/he/fa/hr) | SYLTHARAE file analysis | Localization | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-05 | 2026-10-06 | Completed 2026-10-06 (America/Adak). Map viewer and interface registry strings in all catalogs; .mo compiled. | Translate map and sidebar registry strings for all maintained locales.
Analyst Categorization page strings (banner, filters, pagination, sidebar) | SYLTHARAE file analysis | Localization | No | Completed | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-06 | 2026-10-06 | Completed 2026-10-06 (America/Adak). Banner, placeholders, pagination, taxonomy sidebar text localized. | Fix English fallback on analyst categorization UI strings.
Wire export_surfaces_smoke.py into CI | SYLTHARAE file analysis | DevOps | No | Not started | Medium | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-07 | 2026-10-08 | Planned (America/Adak). Requires SMOKE_ADMIN_PASSWORD and reachable app in pipeline. | Automate export surface checks in continuous integration.
Full pytest table_export / DB integration suite in CI | SYLTHARAE file analysis | QA | No | Not started | Medium | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-07 | 2026-10-09 | Planned (America/Adak). Postgres credentials needed for CI/agent environment. | Run DB-backed export tests in CI reliably.
Browser regression — FMAS export menu, map soft-nav, Arabic RTL spot-check | SYLTHARAE file analysis | QA | No | In progress | High | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-06 | 2026-10-08 | Started 2026-10-06 (America/Adak). Operator sign-off: restart app, hard refresh, set_language ar/he/fa. | Manual regression on critical UI after i18n and button fixes.
Optional — offline catalog download URLs, 3D map, per-file map icons | SYLTHARAE file analysis | Enhancement | No | Not started | Low | SYLTHARAE — File analysis platform completion (Map, exports, i18n, UI QA) | 2026-10-10 | 2026-10-20 | Backlog (America/Adak). Not blocking release. | Future map viewer enhancements from roadmap.